## Slide 1: Asian Harmonization Working Party Technical Committee WG update
30 Nov 2010, Riyadh, Kingdom of Saudi Arabia

## Slide 2: Asian Harmonization Working Party Technical Committee WG 1

## Slide 3: Accomplishments
STED - CSDT Comparison Data
AHWP CSDT-STED Mapping Document

## Slide 4: Next Action Steps
Recommendations on Labelling Requirements
Definition of Manufacturer, Authorisation Representatives etc.
Survey on the adoption of STED or CSDT

## Slide 5: Asian Harmonization Working Party Technical Committee WG 1a

## Slide 6: 2010-2011 Work Plan
Work Item | Deadline
Gap analysis of IVD medical devices regulations in member economies Feasibility study on adoption of the classification and conformity assessment of IVD medical devices proposed by GHTF | Mar 28, 2010 (Extended to Jul 31, 2010)
Liaise to GHTF in developing related documents on clinical evidence for IVD medical devices | Jul 31, 2010 (Extended to Sep ,2010)
Liaise to GHTF in developing related documents on the Essential Principles and labeling of IVD medical devices | Dec 31, 2010
Holding workshop on GHTF documents on IVD medical devices regulations | During 15th AHWP- 12th TC meeting Sunday 28th Nov 2010 by:Dr.Petra Wiele
Feasibility study on the adoption of the IVD STED, definition and concepts on clinical evidence of IVD medical devices proposed by GHTF | Sep, 2011
<number>
Ever since the foundation of this subgroup, we have been working closely with GHTF
in the harmonization of IVD medical devices regulations

## Slide 7: Achievements
AHWP-WG01a has been cooperating with GHTF-SG01a to review or draft the following documents:
    SG1-N45:2008 Principles of In Vitro Diagnostic (IVD) Medical Devices Classification
    SG1-N46:2008 Principles of Conformity Assessment for In Vitro Diagnostic (IVD) Medical Devices
    SG1(PD)/N063 “Summary Technical Documentation (STED) for Demonstrating Conformity to the Essential Principles of Safety and Performance of In Vitro Diagnostic Medical Devices”
    “Clinical Evidence for IVD medical devices–Key Definitions and Concepts” (Draft)
    ”Clinical Evidence for IVD medical devices–Clinical utility and performance evaluation” (Draft)
<number>
The documents were subject to the review of WG01a and comments
were consolidated and reflected in GHTF SG1 IVD Subgroup working meetings.

## Slide 8: Progress (1)
Work Item | Deadline | Status
Gap analysis of IVD medical devices regulation within AHWP member economies Feasibility study on adoption of the classification and conformity assessment of IVD medical devices proposed by GHTF | Mar 28, 2010 (Extended to Jul 31, 2010) | Inputs from 5 member economies have been consolidated.
<number>

## Slide 9: Progress (2)
Work Item | Deadline | Status
Liaise to GHTF in developing the following documents: “Clinical Evidence for IVD medical devices–Key Definitions and Concepts” (Draft) ”Clinical Evidence for IVD medical devices–Clinical utility and performance evaluation” (Draft) | Jul 31, 2010 (Postponed to Nov 30, 2010) | Underway : collecting comments & will be discuss during 6-10 Dec 2010 Ca-meeting.
<number>
Both draft guidance are available upon request. (For internal circulation only.)

## Slide 10: Progress (3)
Work Item | Deadline | Status
Liaise to GHTF in developing documents on the following topics : Essential principles for demonstrating the safety and performance of IVD medical devices Labeling of IVD medical devices (including graphical symbols) | Dec 31, 2010 | Underway: Conducting exercises on the EP for IVD medical devices collected comments will be discussed during Dec, CA-meeting
<number>

## Slide 11: Progress (4)
Work Item | Deadline | Status
Holding workshop on STED for IVD medical devices and various related topics | (28th Nov 2010) | the presenter: Dr. Petra Carls Wiele
<number>

## Slide 12: 2011 Work Plan
Work Item | Deadline
Feasibility study on the adoption of the IVD STED, definition and concepts on clinical evidence of IVD medical devices proposed by GHTF. Proposing the training for IVDMD capacity building needs | Sep, 2011
<number>

## Slide 13: Asian Harmonization Working Party Technical Committee WG 2

## Slide 14
WG2 Key achievements
Dissemination of Saudi's NCMDR on weekly basis (To become effective shortly)
SADS ON-Line Reporting (Trial website available)
Training Material Folder under AHWP Website (Posted already)
Draft Adverse Event Report Form (For comments)
Draft FSCA Report Form (For comments)
Notes: <number>

## Slide 15
Work Plans
Training
  Create the folder under AHWP WG02 & post all the trainings + VDO that need consent form from all the trainers to upload on the folder.
  Proposed structure the trainings
    Basic training
      SG02 guidance documents
      Manufacturers Trend Reporting of Adverse Events
      Guidance of How to handle information concerning Vigilance Reporting Related to Medical Devices
      FSCA
Notes: <number>

## Slide 16
Work Plans
Training (Cont)
    Advance program
      Mark Bruley (ECRI)_AE investigation program
  Plan to VDO taping for the whole training
  After AHWP meeting, plan to provide DVDs to the regulators and industries group for each economy
  Long term_Propose WG06 to take care all these materials distribution
Notes: <number>

## Slide 17: Asian Harmonization Working Party Technical Committee WG 3

## Slide 18: Achievements
Worked with GHTF SG3 to actively developed N17 (Guidance on the control of product and services obtained from suppliers) and N18 (Guidance on corrective action and preventive action).
Reviews by WG3 and AHWP member economies of N17 did not raise any issues that required modification of the document for use by AHWP. As such, WG3 recommends that document be adopted by AHWP with no changes.
Initiated survey on the QMS requirements in AHWP member economies and analyzed data from responses received to date.
Initiated development of N19 (Criteria for characterizing the significance of QMS deficiencies) with GHTF SG3

## Slide 19: Next Steps
Complete QMS survey by obtaining responses from remaining AHWP member economies and analyzing data
Complete development of N19 with GHTF SG3
Review comments and feedback from AHWP on N18 and evaluate for adoption by AHWP
Work with GHTF SG3 and ISO TC210 to evaluate need for revision of ISO 13485 and, if applicable, to work on follow-up activities

## Slide 20: Asian Harmonization Working Party Technical Committee WG 4

## Slide 21: - Action items for WG4 had unclear objectives or guidelines. - working group members proposed to survey the demands of each member economy for auditing.
WG4 members proposed a survey in June.
Developing Questionnaires in July.
Questionnaires review meeting via Telcon in August.
Finalizing and deploy the Questionnaires in September.
Gathering answers from both Industries and Regulators during Oct.– Nov.
7 member economies(China, Chinese Taipei, India, Korea, Malaysia, Saudi Arabia, Singapore) out of 9 have audits and audit regulations.
Improvement areas that member economies see;
  Auditors’ qualification and training
  Audit guidance to be consistent.
  Standardized audit report.
Action Plan in 2010
Survey Results

## Slide 22: - Some opinions look too subjective to represent member economies. - Limited to 9 member economies only. - Expectations are various based on regulations developmental status.
Do we need more feedbacks to have a full picture of audit status of AHWP member economies ?
Do we have to go for ISO standard first or GHTF guidance for auditing for AHWP member economies ?
Feedback on survey results in Dec 2010.
Identify & prioritize key action items for WG4 to focus on in Jan.
Review of ISO or GHTF guidance in Jan – March.
Top priority project kick-off in April.
Progress update on AHWP TC meeting
Delivery the outcome in 16th. AHWP meeting
Some Questions
Plan for 2011

## Slide 23: Asian Harmonization Working Party Technical Committee WG 5

## Slide 24: WG5 - Progress Report
Presented by Gao Jie/Tran Quan (Chair/Co-Chair AHWP WG5)
1. Comparative study of Clinical Trials Regulations & related guidances on Clinical Safety/Performance in AHWP member economies
Review Clinical Trials Regulations or its developments in China, India, Korea, Singapore, Chinese Taipei &Thailand
2. Training Initiatives
Workshop at 10th AHWP TC meeting, Singapore, May 2010
- Painting the Clinical Picture: Clinical Evaluation & Clinical Evidence by
Mr. Greg LeBlance, Vice Chair GHTF SG5
Workshop at 15th AHWP annual meeting, Saudi Arabia, Nov 2010
- ISO14155 by Ms. Danielle Giroud, Convenor TC 194 WG4
3. Review GHTF SG5 Document & make recommendations to AHWP member economies on the feasibilities of adoption
Completed studying and reviewing 5 GHTF SG5 documents (incl. 1 in draft)
4. Set up Advisory Expert Panels of GHTF SG5 members
6 members incl. Chair & Vice Chair; 2 Japan, PMDA officers; 2 Industry experts (EU & Australia)

## Slide 25: Reaching 2011 Milestones - Strategies & Plans
Presented by Gao Jie/Tran Quan (Chair/Co-Chair AHWP WG5)
Leveraging on the Advisory Panel of SG5 experts for training & advice on GHTF SG5 documents review & adoption
  March / April 2011 – Review of Clinical Evidence, Key Definitions & Concepts (SG5/N1R8:2007) & Clinical Evaluation (SG5/N2R8:2007)
  May/June 2011 –Face to face working session ( SG5-WG5)
    Review AHWP guidance document on adoption of GHTF SG5 GN
    Discuss at least one GHTF GN on feasibility of adoption in AHWP member economies
  June-Sept 2011 – Seek preliminary input from member economies on draft GN
  Oct 2011 – Follow up to finalize recommendations for AHWP Annual meeting ‘11
2. Comparative study of Clinical Trials Regulations & related guidances on Clinical Safety/Performance in AHWP member economies
  Deep dive into member economies regulations
  Update survey with new questions
Training Initiatives
  Organize experts to speak on GCP & Declaration of Helsinki at AHWP conferences
  Invite Regulators from Member Economies to discuss Clinical Trial Regulations development & directions
Greater collaborations with other international organizations / Work Groups
  E.g. APEC Harmonization Centre & Harmonization By Doing (USFDA & MHLW, Japan)

## Slide 26: Asian Harmonization Working Party Technical Committee WG 6

## Slide 27: STG Nomenclature Lindsay Tao, Co Chair 15th AHWP Annual Conference, Riyadh, Saudi Arabia

## Slide 28: Achievements
<number>
Nomination of two representatives to Board of Trustee of GMDN
  China SFDA, Mr. Chang Yongheng
  Singapore HSA, Mrs. Christina Lim
Nomination of new Chair of AHWP STG nomenclature
  China SFDA, Mr. Yang Lianchun
AHWP

## Slide 29: Next Step
AHWP
Nomination of 5 PARTICIPANTS from AHWP to be Policy Advisory Group at GMDN
    1 from each of the following members - CHINA, MALAYSIA,SAUDI ARABIA,SINGAPORE,SOUTH KOREA
  Join WHO special work task force on nomenclature
  Work with WHO, GMDN and other stakeholders on a single nomenclature system for medical device
  Working on issues on governance, charging fee transparency, communication and response mechanism of nomenclature system

## Slide 30
Presentation Title Goes Here
<number>
Notes: <number>
2009 Investor Meeting | Deutsche Bank – May, 19, 2009
<number>